## Tracking Report
[30 empty] | Proposal #: | 1539
Job #:
Change #:
[30 empty] | Description: | FLARE #2 METER RELOCATION
[30 empty] | Owner: | CALUMET
[30 empty] | Location: | GREAT FALLS, MT
[30 empty] | Date: | 2023-08-14 11:26
WBS TRACKING REPORT
[17 empty] | RIG | [16 empty] | USE TAX
[17 empty] | 15 | [16 empty] | 0%
WBS | PHASE | SIZE | FLC | LINE / DESCRIP | SPEC | INSUL | INSL. SIZE | SHT | AREA | STATUS | SPCL RATE | SPCL SUB | OWNERSHIP | QTY | UNIT | CRAFT | WELD | SUB | TOTAL | BASE | BURDEN | OVERHEAD | LABOR PROFIT | FUEL | CNSMBLE | SUBSIST | LABOR | RIGS | MATERIAL | EQUIP | SUBS | COST ONLY | PROFIT TOTAL (R/M/E/S) | SALES TAX | TOTAL
[17 empty] | 40.7 |  |  | 37.35 | 21.05% | 10% | 10% | 3% | 10% | 14 |  | 10% | 7.5% | 7.5% | 7.5% | (no tax or mu) |  | 0%
10000 |  |  |  | MOBILIZE | [9 empty] | 1 | EA | 60 | 30 | 0 | 90 | 3484.5 | 733.4873 | 348.45 | 348.45 | 104.535 | 348.45 | 1260 | 6627.8723 | 450 | 0 | 0 | 0 | 3650 | 45 | 0 | 10772.8723
| 10003 |  |  | TRAVEL IN | [9 empty] | 2 | CRAFT | 20 | 10 | 0 | 30 | 1176.5 | 247.6532 | 117.65 | 117.65 | 35.295 | 117.65 | 420 | 2232.3983 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 2397.3983
| 10003 |  |  | TRAVEL IN - QC | [6 empty] | 39.6 | 14 |  | 1 | CRAFT | 10 | 0 | 0 | 10 | 396 | 83.358 | 39.6 | 39.6 | 11.88 | 39.6 | 140 | 750.038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.038
| 10003 |  |  | TRAVEL IN - CRAFT | [9 empty] | 1 | CRAFT | 10 | 10 | 0 | 20 | 780.5 | 164.2952 | 78.05 | 78.05 | 23.415 | 78.05 | 280 | 1482.3602 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 1647.3602
| 10004 |  |  | SAFETY ORIENTATION | [9 empty] | 5 | CRAFT | 40 | 10 | 0 | 50 | 1901 | 400.1605 | 190.1 | 190.1 | 57.03 | 190.1 | 700 | 3628.4905 | 150 | 0 | 0 | 0 | 1250 | 15 | 0 | 5043.4905
| 10004 |  |  | DRUG TESTING | [9 empty] | 5 | CRAFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 1250
| 10004 |  |  | CUSTOMER SAFETY ORIENTATION | [9 empty] | 4 | CRAFT | 40 | 0 | 0 | 40 | 1494 | 314.487 | 149.4 | 149.4 | 44.82 | 149.4 | 560 | 2861.507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861.507
| 10004 |  |  | CUSTOMER SAFETY ORIENTATION | [9 empty] | 1 | WELD | 0 | 10 | 0 | 10 | 407 | 85.6735 | 40.7 | 40.7 | 12.21 | 40.7 | 140 | 766.9835 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 931.9835
| 10005 |  |  | WELDER TEST / QUALIFICATION | [9 empty] | 1 | WELD | 0 | 10 | 0 | 10 | 407 | 85.6735 | 40.7 | 40.7 | 12.21 | 40.7 | 140 | 766.9835 | 150 | 0 | 0 | 0 | 500 | 15 | 0 | 1431.9835
| 10005 |  |  | TEST COUPONS | [9 empty] | 1 | WELD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500
| 10005 |  |  | TEST | [9 empty] | 1 | WELD | 0 | 10 | 0 | 10 | 407 | 85.6735 | 40.7 | 40.7 | 12.21 | 40.7 | 140 | 766.9835 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 931.9835
| 10008 |  |  | FREIGHT IN | [9 empty] | 4 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 1900
| 10008 |  |  | MANLIFT FREIGHT IN | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 150
| 10008 |  |  | FORKLIFT FREIGHT IN | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500
| 10008 |  |  | AIR COMPRESSOR FREIGHT IN | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500
| 10008 |  |  | TOOL VAN FREIGHT IN | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750
20000 |  |  |  | SITE PREPARATION | [9 empty] | 2 | CY | 4.45 | 0 | 0 | 4.45 | 166.2075 | 34.9867 | 16.6208 | 16.6208 | 4.9862 | 16.6208 | 62.3 | 318.3427 | 0 | 100 | 0 | 0 | 0 | 7.5 | 0 | 425.8427
| 20001 |  |  | LADDER LANDING EXCAVATION | [9 empty] | 1 | CY | 3 | 0 | 0 | 3 | 112.05 | 23.5865 | 11.205 | 11.205 | 3.3615 | 11.205 | 42 | 214.613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.613
| 20001 |  |  | EXCAVATE, HEAVY (CLASS B/C - SOIL) | [9 empty] | 1 | CY | 3 | 0 | 0 | 3 | 112.05 | 23.5865 | 11.205 | 11.205 | 3.3615 | 11.205 | 42 | 214.613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.613
| 20002 |  |  | LADDER LANDING BACK FILL | [9 empty] | 1 | CY | 1.45 | 0 | 0 | 1.45 | 54.1575 | 11.4002 | 5.4158 | 5.4158 | 1.6247 | 5.4158 | 20.3 | 103.7296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.7296
| 20002 |  |  | BACKFILL / COMPACT - HEAVY (CLASS C - CLASS 5/13) | [9 empty] | 1 | CY | 1.45 | 0 | 0 | 1.45 | 54.1575 | 11.4002 | 5.4158 | 5.4158 | 1.6247 | 5.4158 | 20.3 | 103.7296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.7296
| 29999 |  |  | MATERIAL | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 7.5 | 0 | 107.5
| 29999 |  |  | FILL MATERIAL (FAGENSTROM) | [9 empty] | 1 | CY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 7.5 | 0 | 107.5
60000 |  |  |  | STRUCTURAL | [9 empty] | 5 | TON | 236.69 | 0 | 0 | 236.69 | 8840.3715 | 1860.8982 | 884.0372 | 884.0372 | 265.2111 | 884.0372 | 3313.66 | 40382.3022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27237.385
| 60001 |  |  | FABRICATE STEEL | [9 empty] | 1 | TON | 32.54 | 0 | 0 | 32.54 | 1215.369 | 255.8352 | 121.5369 | 121.5369 | 36.4611 | 121.5369 | 455.56 | 2327.8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2327.8359
| 60001 |  |  | OFFLOAD MATERIALS | [9 empty] | 1 | TON | 2 | 0 | 0 | 2 | 74.7 | 15.7243 | 7.47 | 7.47 | 2.241 | 7.47 | 28 | 143.0754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.0754
| 60001 |  |  | FLAME CUTTING - 3/16 THK. - 5/16 THK. | [9 empty] | 6 | LF | 0.54 | 0 | 0 | 0.54 | 20.169 | 4.2456 | 2.0169 | 2.0169 | 0.60507 | 2.0169 | 7.56 | 38.6303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.6303
| 60001 |  |  | DRILL BEAMS | [9 empty] | 24 | EA | 12 | 0 | 0 | 12 | 448.2 | 94.3461 | 44.82 | 44.82 | 13.446 | 44.82 | 168 | 858.4521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 858.4521
| 60001 |  |  | FABRICATE MOUNTING PLATES | [9 empty] | 24 | EA | 18 | 0 | 0 | 18 | 672.3 | 141.5191 | 67.23 | 67.23 | 20.169 | 67.23 | 252 | 1287.6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287.6781
| 60002 |  |  | FABRICATE LADDERS | [9 empty] | 1 | TON | 28.25 | 0 | 0 | 28.25 | 1055.1375 | 222.1064 | 105.5138 | 105.5138 | 31.6541 | 105.5138 | 395.5 | 15033.6424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020.9393
| 60002 |  |  | OFFLOAD MATERIAL | [9 empty] | 1 | TON | 2 | 0 | 0 | 2 | 74.7 | 15.7243 | 7.47 | 7.47 | 2.241 | 7.47 | 28 | 143.0754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.0754
| 60002 |  |  | FABRICATE STRAIGHT LADDERS | [9 empty] | 0.25 | TON | 26.25 | 0 | 0 | 26.25 | 980.4375 | 206.3821 | 98.0438 | 98.0438 | 29.4131 | 98.0438 | 367.5 | 1877.864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1877.864
| 60003 |  |  | FABRICATE HANDRAIL | [9 empty] | 1 | TON | 34 | 0 | 0 | 34 | 1269.9 | 267.3139 | 126.99 | 126.99 | 38.097 | 126.99 | 476 | 12869.6277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2432.281
| 60003 |  |  | OFFLOAD MATERIAL | [9 empty] | 1 | TON | 2 | 0 | 0 | 2 | 74.7 | 15.7243 | 7.47 | 7.47 | 2.241 | 7.47 | 28 | 143.0754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.0754
| 60003 |  |  | FABRICATE HANDRAIL W/ TOE PLATE | [9 empty] | 64 | LF | 32 | 0 | 0 | 32 | 1195.2 | 251.5896 | 119.52 | 119.52 | 35.856 | 119.52 | 448 | 2289.2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2289.2056
| 60004 |  |  | INSTALL PLATFORM | [9 empty] | 2 | TON | 141.9 | 0 | 0 | 141.9 | 5299.965 | 1115.6426 | 529.9965 | 529.9965 | 158.999 | 529.9965 | 1986.6 | 10151.1961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10151.1961
| 60004 |  |  | INSTALL SAFETY CHAIN | [9 empty] | 2 | EA | 4 | 0 | 0 | 4 | 149.4 | 31.4487 | 14.94 | 14.94 | 4.482 | 14.94 | 56 | 286.1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1507
| 60004 |  |  | INSTALL SAFETY GATES | [9 empty] | 2 | EA | 4 | 0 | 0 | 4 | 149.4 | 31.4487 | 14.94 | 14.94 | 4.482 | 14.94 | 56 | 286.1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1507
| 60004 |  |  | GRATING - 1-1/4 X 3/16 (9.2 LBS/SF) | [9 empty] | 240 | SF | 48 | 0 | 0 | 48 | 1792.8 | 377.3844 | 179.28 | 179.28 | 53.784 | 179.28 | 672 | 3433.8084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3433.8084
| 60004 |  |  | OFFLOAD | [9 empty] | 2 | TON | 3 | 0 | 0 | 3 | 112.05 | 23.5865 | 11.205 | 11.205 | 3.3615 | 11.205 | 42 | 214.613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.613
| 60004 |  |  | SHAKEOUT | [9 empty] | 2 | TON | 4 | 0 | 0 | 4 | 149.4 | 31.4487 | 14.94 | 14.94 | 4.482 | 14.94 | 56 | 286.1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1507
| 60004 |  |  | ERECT (0-20 LBS/FT) | [9 empty] | 0.5 | TON | 17.5 | 0 | 0 | 17.5 | 653.625 | 137.5881 | 65.3625 | 65.3625 | 19.6088 | 65.3625 | 245 | 1251.9093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1251.9093
| 60004 |  |  | HANDRAIL & TOEPLATE | [9 empty] | 64 | LF | 44.8 | 0 | 0 | 44.8 | 1673.28 | 352.2254 | 167.328 | 167.328 | 50.1984 | 167.328 | 627.2 | 3204.8878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3204.8878
| 60004 |  |  | LADDERS & CAGES | [9 empty] | 12 | LF | 12.6 | 0 | 0 | 12.6 | 470.61 | 99.0634 | 47.061 | 47.061 | 14.1183 | 47.061 | 176.4 | 901.3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 901.3747
| 60004 |  |  | CLEAN UP | [9 empty] | 2 | TON | 4 | 0 | 0 | 4 | 149.4 | 31.4487 | 14.94 | 14.94 | 4.482 | 14.94 | 56 | 286.1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286.1507
| 69999 |  |  | MATERIAL | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10305.1328
| 69999 |  |  | WEDGES | [9 empty] | 12 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435.6 | 0 | 0 | 0 | 32.67 | 0 | 468.27
| 69999 |  |  | SAFETY GATE | [9 empty] | 2 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426 | 0 | 0 | 0 | 31.95 | 0 | 457.95
| 69999 |  |  | HANDRAIL & STEEL MEMBERS | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914.57 | 0 | 0 | 0 | 218.5927 | 0 | 3133.1627
| 69999 |  |  | SAFETY CHAIN | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 15 | 0 | 215
| 69999 |  |  | GRATING | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | 0 | 0 | 0 | 356.25 | 0 | 5106.25
| 69999 |  |  | MISC. 10% | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 0 | 0 | 0 | 64.5 | 0 | 924.5
70000 |  |  |  | AG PIPING | [9 empty] | 8 | LF | 88.72 | 50 | 0 | 138.72 | 5348.692 | 1125.8997 | 534.8692 | 534.8692 | 160.4608 | 534.8692 | 1942.08 | 10181.74 | 750 | 1547.25 | 0 | 25077 | 400 | 2071.8187 | 0 | 40027.8088
| 70001 | 24 | HL | 7332 | A2 |  |  | 1 | [5 empty] | 4 | LF | 26.92 | 9.2 | 0 | 36.12 | 1379.902 | 290.4694 | 137.9902 | 137.9902 | 41.3971 | 137.9902 | 505.68 | 2631.419 | 138 | 0 | 0 | 0 | 0 | 13.8 | 0 | 2783.219
| 70001 |  |  | HE - 3 | [9 empty] | 4 | LF | 0.92 | 0 | 0 | 0.92 | 34.362 | 7.2332 | 3.4362 | 3.4362 | 1.0309 | 3.4362 | 12.88 | 65.8147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.8147
| 70001 |  |  | FW - 3 | [9 empty] | 4 | EA | 8 | 9.2 | 0 | 17.2 | 673.24 | 141.717 | 67.324 | 67.324 | 20.1972 | 67.324 | 240.8 | 1277.9262 | 138 | 0 | 0 | 0 | 0 | 13.8 | 0 | 1429.7262
| 70001 |  |  | V - 3 | [9 empty] | 8 | EA | 10 | 0 | 0 | 10 | 373.5 | 78.6217 | 37.35 | 37.35 | 11.205 | 37.35 | 140 | 715.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715.3768
| 70001 |  |  | BU - 3 | [9 empty] | 8 | EA | 8 | 0 | 0 | 8 | 298.8 | 62.8974 | 29.88 | 29.88 | 8.964 | 29.88 | 112 | 572.3014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572.3014
| 70002 | 24 | HL | 7332 | A2 |  |  | 2 | [5 empty] | 4 | LF | 16.8 | 10.8 | 0 | 27.6 | 1067.04 | 224.6119 | 106.704 | 106.704 | 32.0112 | 106.704 | 386.4 | 2030.1751 | 162 | 0 | 0 | 0 | 0 | 16.2 | 0 | 2208.3751
| 70002 |  |  | HE - ≤2 | [9 empty] | 4 | LF | 0.8 | 0 | 0 | 0.8 | 29.88 | 6.2897 | 2.988 | 2.988 | 0.8964 | 2.988 | 11.2 | 57.2301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2301
| 70002 |  |  | SW - 1.5 | [9 empty] | 3 | EA | 2.25 | 2.25 | 0 | 4.5 | 175.6125 | 36.9664 | 17.5613 | 17.5613 | 5.2684 | 17.5613 | 63 | 333.5311 | 33.75 | 0 | 0 | 0 | 0 | 3.375 | 0 | 370.6561
| 70002 |  |  | SW - 1 | [9 empty] | 3 | EA | 1.5 | 1.5 | 0 | 3 | 117.075 | 24.6443 | 11.7075 | 11.7075 | 3.5123 | 11.7075 | 42 | 222.354 | 22.5 | 0 | 0 | 0 | 0 | 2.25 | 0 | 247.104
| 70002 |  |  | SW - ≤.75 | [9 empty] | 4 | EA | 1.6 | 1.6 | 0 | 3.2 | 124.88 | 26.2872 | 12.488 | 12.488 | 3.7464 | 12.488 | 44.8 | 237.1776 | 24 | 0 | 0 | 0 | 0 | 2.4 | 0 | 263.5776
| 70002 |  |  | FSW - 1.5 | [9 empty] | 1 | EA | 1 | 1 | 0 | 2 | 78.05 | 16.4295 | 7.805 | 7.805 | 2.3415 | 7.805 | 28 | 148.236 | 15 | 0 | 0 | 0 | 0 | 1.5 | 0 | 164.736
| 70002 |  |  | FSW - 1 | [9 empty] | 1 | EA | 0.7 | 0.7 | 0 | 1.4 | 54.635 | 11.5007 | 5.4635 | 5.4635 | 1.639 | 5.4635 | 19.6 | 103.7652 | 10.5 | 0 | 0 | 0 | 0 | 1.05 | 0 | 115.3152
| 70002 |  |  | OL - 1.5 | [9 empty] | 1 | EA | 2 | 2 | 0 | 4 | 156.1 | 32.8591 | 15.61 | 15.61 | 4.683 | 15.61 | 56 | 296.4721 | 30 | 0 | 0 | 0 | 0 | 3 | 0 | 329.4721
| 70002 |  |  | OL - 1 | [9 empty] | 1 | EA | 1.75 | 1.75 | 0 | 3.5 | 136.5875 | 28.7517 | 13.6588 | 13.6588 | 4.0976 | 13.6588 | 49 | 259.413 | 26.25 | 0 | 0 | 0 | 0 | 2.625 | 0 | 288.288
| 70002 |  |  | V - ≤2 | [9 empty] | 6 | EA | 3 | 0 | 0 | 3 | 112.05 | 23.5865 | 11.205 | 11.205 | 3.3615 | 11.205 | 42 | 214.613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.613
| 70002 |  |  | BU - ≤2 | [9 empty] | 2 | EA | 1.5 | 0 | 0 | 1.5 | 56.025 | 11.7933 | 5.6025 | 5.6025 | 1.6808 | 5.6025 | 21 | 107.3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.3065
| 70002 |  |  | THRD - 1 | [9 empty] | 1 | EA | 0.3 | 0 | 0 | 0.3 | 11.205 | 2.3587 | 1.1205 | 1.1205 | 0.33615 | 1.1205 | 4.2 | 21.4613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.4613
| 70002 |  |  | THRD - ≤.75 | [9 empty] | 2 | EA | 0.4 | 0 | 0 | 0.4 | 14.94 | 3.1449 | 1.494 | 1.494 | 0.4482 | 1.494 | 5.6 | 28.6151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.6151
| 70003 |  |  | FIELD VERIFY | [9 empty] | 1 | EA | 10 | 10 | 0 | 20 | 780.5 | 164.2952 | 78.05 | 78.05 | 23.415 | 78.05 | 280 | 1482.3602 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 1647.3602
| 70003 |  |  | FIELD VERIFY | [9 empty] | 1 | EA | 10 | 10 | 0 | 20 | 780.5 | 164.2952 | 78.05 | 78.05 | 23.415 | 78.05 | 280 | 1482.3602 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 1647.3602
| 79992 |  |  | HOT TAPS | [9 empty] | 6 | EA | 20 | 20 | 0 | 40 | 1561 | 328.5905 | 156.1 | 156.1 | 46.83 | 156.1 | 560 | 2964.7205 | 300 | 0 | 0 | 21577 | 400 | 1648.275 | 0 | 26889.9955
| 79992 |  |  | POW | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 400
| 79992 |  |  | TEAM INC. | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21577 | 0 | 1618.275 | 0 | 23195.275
| 79992 |  |  | INDEMAND SUPPORT CREW | [9 empty] | 2 | DAY | 20 | 20 | 0 | 40 | 1561 | 328.5905 | 156.1 | 156.1 | 46.83 | 156.1 | 560 | 2964.7205 | 300 | 0 | 0 | 0 | 0 | 30 | 0 | 3294.7205
| 79993 |  |  | NDE | [9 empty] | 6 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 262.5 | 0 | 3762.5
| 79993 |  |  | NDE | [9 empty] | 1 | DAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 262.5 | 0 | 3762.5
| 79996 |  |  | HYDROTESTING | [9 empty] | 6 | EA | 15 | 0 | 0 | 15 | 560.25 | 117.9326 | 56.025 | 56.025 | 16.8075 | 56.025 | 210 | 1073.0651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073.0651
| 79996 |  |  | HYDRO - 3 | [9 empty] | 4 | EA | 10 | 0 | 0 | 10 | 373.5 | 78.6217 | 37.35 | 37.35 | 11.205 | 37.35 | 140 | 715.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715.3768
| 79996 |  |  | HYDRO - ≤2 | [9 empty] | 2 | EA | 5 | 0 | 0 | 5 | 186.75 | 39.3109 | 18.675 | 18.675 | 5.6025 | 18.675 | 70 | 357.6884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.6884
| 79999 |  |  | MATERIAL | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547.25 | 0 | 0 | 0 | 116.0438 | 0 | 1663.2938
| 79999 |  |  | PIPING MATERIALS | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407.25 | 0 | 0 | 0 | 105.5438 | 0 | 1512.7938
| 79999 |  |  | MISC. 10% | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 10.5 | 0 | 150.5
110000 |  |  |  | PAINTING | [9 empty] | 491 | SF | 79.56 | 0 | 0 | 79.56 | 2971.566 | 625.5146 | 297.1566 | 297.1566 | 89.147 | 297.1566 | 1113.84 | 5691.5374 | 0 | 1860 | 0 | 0 | 0 | 139.5 | 0 | 7691.0374
| 110001 |  |  | PAINT | [9 empty] | 488 | SF | 79.56 | 0 | 0 | 79.56 | 2971.566 | 625.5146 | 297.1566 | 297.1566 | 89.147 | 297.1566 | 1113.84 | 5691.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5691.5374
| 110001 |  |  | PAINT STRUCTURAL | [9 empty] | 488 | SF | 29.28 | 0 | 0 | 29.28 | 1093.608 | 230.2045 | 109.3608 | 109.3608 | 32.8082 | 109.3608 | 409.92 | 2094.6231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094.6231
| 110001 |  |  | PAINT PIPING | [9 empty] | 6 | EA | 10.5 | 0 | 0 | 10.5 | 392.175 | 82.5528 | 39.2175 | 39.2175 | 11.7652 | 39.2175 | 147 | 751.1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 751.1456
| 110001 |  |  | PREP STRUCTURAL | [9 empty] | 488 | SF | 29.28 | 0 | 0 | 29.28 | 1093.608 | 230.2045 | 109.3608 | 109.3608 | 32.8082 | 109.3608 | 409.92 | 2094.6231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094.6231
| 110001 |  |  | PREP PIPING | [9 empty] | 6 | EA | 10.5 | 0 | 0 | 10.5 | 392.175 | 82.5528 | 39.2175 | 39.2175 | 11.7652 | 39.2175 | 147 | 751.1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 751.1456
| 119999 |  |  | MATERIAL | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860 | 0 | 0 | 0 | 139.5 | 0 | 1999.5
| 119999 |  |  | ZINC CLAD PRIMER | [9 empty] | 5 | GAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 39.375 | 0 | 564.375
| 119999 |  |  | MACROPOXY 646 | [9 empty] | 5 | GAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 29.25 | 0 | 419.25
| 119999 |  |  | PAINTING EQUIPMENT | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 56.25 | 0 | 806.25
| 119999 |  |  | THINNER | [9 empty] | 3 | GAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 0 | 0 | 14.625 | 0 | 209.625
120000 |  |  |  | DISMANTLING | [9 empty] | 4 | SF | 10 | 0 | 0 | 10 | 373.5 | 78.6217 | 37.35 | 37.35 | 11.205 | 37.35 | 140 | 715.3768 | 0 | 231.92 | 0 | 0 | 0 | 17.394 | 0 | 964.6908
| 120001 |  |  | DEMO EXISTING INSTRUMENTS | [9 empty] | 3 | EA | 10 | 0 | 0 | 10 | 373.5 | 78.6217 | 37.35 | 37.35 | 11.205 | 37.35 | 140 | 715.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715.3768
| 120001 |  |  | UNBOLT AND REMOVE TRANSDUCERS | [9 empty] | 2 | EA | 5 | 0 | 0 | 5 | 186.75 | 39.3109 | 18.675 | 18.675 | 5.6025 | 18.675 | 70 | 357.6884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.6884
| 120001 |  |  | DISCONNECT PI 07651 | [9 empty] | 1 | EA | 2.5 | 0 | 0 | 2.5 | 93.375 | 19.6554 | 9.3375 | 9.3375 | 2.8013 | 9.3375 | 35 | 178.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178.8442
| 120001 |  |  | DISCONNECT TI 07731 | [9 empty] | 1 | EA | 2.5 | 0 | 0 | 2.5 | 93.375 | 19.6554 | 9.3375 | 9.3375 | 2.8013 | 9.3375 | 35 | 178.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178.8442
| 129999 |  |  | MATERIAL | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231.92 | 0 | 0 | 0 | 17.394 | 0 | 249.314
| 129999 |  |  | BLINDING MATERIALS | [9 empty] | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231.92 | 0 | 0 | 0 | 17.394 | 0 | 249.314
180000 |  |  |  | SPECIALTY SERVICES | [9 empty] | 1 | EA | 100 | 0 | 0 | 100 | 2750 | 578.875 | 275 | 275 | 82.5 | 275 | 1400 | 5636.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5636.375
| 180002 |  |  | FIREWATCH | [9 empty] | 2 | WEEK | 100 | 0 | 0 | 100 | 2750 | 578.875 | 275 | 275 | 82.5 | 275 | 1400 | 5636.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5636.375
| 180002 |  |  | WEEK (50) | [6 empty] | 27.5 | 14 |  | 2 | WEEK | 100 | 0 | 0 | 100 | 2750 | 578.875 | 275 | 275 | 82.5 | 275 | 1400 | 5636.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5636.375
190000 |  |  |  | DEMOBILIZE | [9 empty] | 1 | EA | 40 | 10 | 0 | 50 | 1923.5 | 404.8967 | 192.35 | 192.35 | 57.705 | 192.35 | 700 | 3663.1518 | 150 | 0 | 0 | 0 | 1900 | 15 | 0 | 5728.1518
| 190001 |  |  | SITE CLEAN UP | [9 empty] | 1 | EA | 20 | 0 | 0 | 20 | 747 | 157.2435 | 74.7 | 74.7 | 22.41 | 74.7 | 280 | 1430.7535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430.7535
| 190001 |  |  | POST CONSTRUCTION | [9 empty] | 1 | EA | 20 | 0 | 0 | 20 | 747 | 157.2435 | 74.7 | 74.7 | 22.41 | 74.7 | 280 | 1430.7535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430.7535
| 190004 |  |  | TRAVEL OUT - SECOND MOB | [9 empty] | 1 | EA | 20 | 10 | 0 | 30 | 1176.5 | 247.6532 | 117.65 | 117.65 | 35.295 | 117.65 | 420 | 2232.3983 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 2397.3983
| 190004 |  |  | TRAVEL OUT - QC | [6 empty] | 39.6 | 14 |  | 2 | WEEK | 10 | 0 | 0 | 10 | 396 | 83.358 | 39.6 | 39.6 | 11.88 | 39.6 | 140 | 750.038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750.038
| 190004 |  |  | TRAVEL OUT - CRAFT (ALT) | [9 empty] | 1 | CRAFT | 10 | 10 | 0 | 20 | 780.5 | 164.2952 | 78.05 | 78.05 | 23.415 | 78.05 | 280 | 1482.3602 | 150 | 0 | 0 | 0 | 0 | 15 | 0 | 1647.3602
| 190006 |  |  | FREIGHT OUT | [9 empty] | 4 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 1900
| 190006 |  |  | TOOL VAN FREIGHT OUT | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750
| 190006 |  |  | MANLIFT FREIGHT OUT | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 150
| 190006 |  |  | FORKLIFT FREIGHT OUT | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500
| 190006 |  |  | AIR COMPRESSOR FREIGHT OUT | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 500
200200 |  |  |  | SUPPORT | [9 empty] | 1 | EA | 150 | 0 | 0 | 150 | 8910 | 1875.555 | 891 | 891 | 267.3 | 891 | 2450 | 16175.855 | 0 | 0 | 5671.9 | 0 | 3522.69 | 425.3925 | 0 | 25795.8375
| 200200 |  |  | PROJECT SUPERINTENDENT | [9 empty] | 2 | WEEK | 100 | 0 | 0 | 100 | 6930 | 1458.765 | 693 | 693 | 207.9 | 693 | 1750 | 12425.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12425.665
| 200200 |  |  | WEEK (50 HRS) | [6 empty] | 69.3 | 17.5 |  | 2 | WEEK | 100 | 0 | 0 | 100 | 6930 | 1458.765 | 693 | 693 | 207.9 | 693 | 1750 | 12425.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12425.665
| 200900 |  |  | QUALITY CONTROL | [9 empty] | 1 | WEEK | 50 | 0 | 0 | 50 | 1980 | 416.79 | 198 | 198 | 59.4 | 198 | 700 | 3750.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750.19
| 200900 |  |  | WEEK (50 HRS) | [6 empty] | 39.6 | 14 |  | 1 | WEEK | 50 | 0 | 0 | 50 | 1980 | 416.79 | 198 | 198 | 59.4 | 198 | 700 | 3750.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750.19
| 209999 |  |  | EQUIPMENT | [9 empty] | 15 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5671.9 | 0 | 3522.69 | 425.3925 | 0 | 9619.9825
| 209999 |  |  | POW | [9 empty] | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.69 | 0 | 0 | 2.69
| 209999 |  |  | AIR COMPRESSOR - ENGINE DRIVEN | [8 empty] | RENTAL | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741 | 0 | 0 | 55.575 | 0 | 796.575
| 209999 |  |  | FORKLIFT - EXTENDA BOOM; 8000#-10000# | [8 empty] | RENTAL | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3580 | 0 | 0 | 268.5 | 0 | 3848.5
| 209999 |  |  | MANLIFT - 60' | [8 empty] | RENTAL | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350.9 | 0 | 0 | 101.3175 | 0 | 1452.2175
| 209999 |  |  | MONITOR - 4 GAS AREA | [8 empty] | OWNED | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 0 | 0 | 640
| 209999 |  |  | MONITOR - H2S PERSONAL | [8 empty] | OWNED | 6 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 480
| 209999 |  |  | PICKUP - 1/2 TO 3/4 TON - QC | [8 empty] | OWNED | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 320
| 209999 |  |  | PICKUP - 1/2 TO 3/4 TON | [8 empty] | OWNED | 2 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280 | 0 | 0 | 1280
| 209999 |  |  | TRAILER - TOOL VAN | [8 empty] | OWNED | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 800
|  |  |  | FLARE #2 METER RELOCATION | [11 empty] | 769.42 | 90 | 0 | 859.42 | 34768.337 | 7318.7349 | 3476.8337 | 3476.8337 | 1043.0501 | 3476.8337 | 12381.88 | 89392.553 | 1350 | 3739.17 | 5671.9 | 25077 | 9472.69 | 2721.6052 | 0 | 124280.0011